## Project Timelines
Project | Sub-project | Task | Owner | Scheduled Date | Completed In Days from Scheduled Date
New Loyalty Scheme | Marketing | Scope | Tom | 2021-04-19 | 0
New Loyalty Scheme | Marketing | Build | Tom | 2021-04-21 | 2
New Loyalty Scheme | Marketing | Deliver | Tom | 2021-04-30 | 5
New Loyalty Scheme | Operations | Scope | Jenny | 2021-04-15 | 0
New Loyalty Scheme | Operations | Build | Jenny | 2021-04-23 | 3
New Loyalty Scheme | Operations | Deliver | Jenny | 2021-04-28 | 4
Spring Sale | Marketing | Scope | Carl | 2021-04-22 | 0
Spring Sale | Marketing | Build | Carl | 2021-04-29 | 6
Spring Sale | Marketing | Deliver | Carl | 2021-05-04 | 3
Spring Sale | Operations | Scope | Jonathan | 2021-04-25 | 0
Spring Sale | Operations | Build | Jonathan | 2021-04-28 | 2
Spring Sale | Operations | Deliver | Jonathan | 2021-05-02 | 4
New Trolley Inventory | Marketing | Scope | Tom | 2021-05-02 | 0
New Trolley Inventory | Marketing | Build | Tom | 2021-05-04 | 3
New Trolley Inventory | Marketing | Deliver | Tom | 2021-05-12 | 5
New Trolley Inventory | Operations | Scope | Jenny | 2021-04-30 | 0
New Trolley Inventory | Operations | Build | Jenny | 2021-05-05 | 2
New Trolley Inventory | Operations | Deliver | Jenny | 2021-05-11 | 6